## flights
Type | Priority | Name | Last Flown | Departure | Arrival | Time (hr) | ICESat/ICESat-2 tracks | Remaining design issues
Land ice | Baseline | Hamilton Line 1 | 2016 | South Pole | South Pole | 4.4 | more than half of all IS-2 and C2-2 tracks | create latlon file
Land ice | Baseline | Hamilton Line 2 | 2016 | South Pole | South Pole | 4.2 | more than half of all IS-2 and C2-2 tracks | create latlon file
Land ice | High | TAM East | new | South Pole | South Pole | 5.5 |  | create latlon file
Land ice | High | TAM Gate East Low | new | South Pole | South Pole | 5.8 |  | align radials with PolarGap lines; create latlon file
Land ice | High | ITASE | new | South Pole | McMurdo | 5.6 |  | create latlon file
Land ice | High | TAM Grounding Line West | new | McMurdo | McMurdo | 5.5 |  | create latlon file
Land ice | High | David A | unknown | McMurdo | McMurdo | 5.7 |  | create latlon file
Land ice | High | Victoria D | new | McMurdo | McMurdo | 5.8 | 0396,0024 (IS-1) | create latlon file
Land ice | High | George V Gap B | new | Dumont d'Urville | Dumont d'Urville | 5.6 |  | create latlon file
Land ice | High | Cook A | new | Dumont d'Urville | Dumont d'Urville | 5.2 |  | create latlon file
Land ice | Medium | TAM Central | 2013 | South Pole | South Pole | 5.6 |  | create latlon file
Land ice | Medium | Ross flowlines | new | McMurdo | McMurdo | 5.4 |  | create latlon file
Land ice | Medium | TAM West | new | McMurdo | McMurdo | 5.2 |  | create latlon file
Land ice | Medium | TAM West Flux | new | McMurdo | McMurdo | 5.1 |  | create latlon file
Land ice | Medium | Cape Adare A | new | McMurdo | McMurdo | 5.8 |  | create latlon file
Land ice | Medium | Victoria A | 2013 | McMurdo | McMurdo | 5.8 | 0128 (IS-1) | create latlon file
Land ice | Medium | Matusevich A | new | Dumont d'Urville | Dumont d'Urville | 5.2 |  | create latlon file
Land ice | Medium | Ninnis A | new | Dumont d'Urville | Dumont d'Urville | 5.3 |  | create latlon file
Land ice | Medium | Dibble-Frost A | new | Dumont d'Urville | Dumont d'Urville | 5.7 |  | create latlon file
Land ice | Low | TAM Gate East High | new | South Pole | South Pole | 5.8 |  | align radials with PolarGap lines; create latlon file
Land ice | Low | Northwest Ross A | new | McMurdo | McMurdo | 5.3 | 70488,70747,71006,70381 (IS-2) | create latlon file
Land ice | Low | Northwest Ross B | new | McMurdo | McMurdo | 5.4 | 70869,70244,70503,70762 (IS-2) | create latlon file
Land ice | Low | TAM Gate West | 2013 | McMurdo | McMurdo | 5.1 |  | create latlon file
Land ice | Low | David B | unknown | McMurdo | McMurdo | 4.9 |  | create latlon file
Land ice | Low | Victoria B | 2013 | McMurdo | McMurdo | 5.5 | 0381,0009 (IS-1) | create latlon file
Land ice | Low | Victoria C | new | McMurdo | McMurdo | 5.7 | 0143,0262 (IS-1) | create latlon file
Land ice | Low | George V Gap A | new | Dumont d'Urville | Dumont d'Urville | 5.7 |  | create latlon file
145.8