## flights
Type | Priority | Name | Last Flown | Departure | Arrival | Time (hr) | ICESat/ICESat-2 tracks | Remaining design issues
Sea ice | Baseline | Laxon Line | 2016 | Thule | Fairbanks | 8.6 | 0329,0328,0334
Sea ice | Baseline | South Basin Transect | 2016 | Fairbanks | Thule | 8.1 | 0282,0284
Sea Ice | High | Chukchi West | new | Fairbanks | Fairbanks | 7.9
Sea Ice | High | East Beaufort | 2015 | Fairbanks | Fairbanks | 8 | 1279
Sea ice | High | North Canada Basin | 2014 | Thule | Thule | 8.1
Sea ice | High | CryoVex | new | Thule | Thule | 5.9 |  | This mission is a placeholder – details will be determined once the CryoVex teams are in the field.
Sea ice | High | North Pole Transect | 2016 | Thule | Thule | 7.7 |  | select contemporaneous, nearby descending CS-2 groundtrack if available
Sea ice | High | Zigzag East | 2015 | Thule | Longyearbyen | 7.2
Sea ice | High | Svalbard North | new | Longyearbyen | Longyearbyen | 8.2 | 0328 | possible coordination with "Barneo" camp (Bernice Notenboom email 26 January 0713)
Sea ice | High | Svalbard South | new | Longyearbyen | Longyearbyen | 7.7 | 0507
Sea ice | Medium | Inner Beaufort Loop | new | Fairbanks | Fairbanks | 6.9 | 1158, 0106
Sea ice | Medium | North Beaufort Loop | 2015 | Fairbanks | Fairbanks | 8 | 1052, 1173
Sea ice | Medium | South Canada Basin | 2016 | Thule | Thule | 7.6
Sea ice | Medium | Zigzag West | 2015 | Thule | Thule | 7.6 |  | select contemporaneous, nearby ascending CS-2 groundtrack if available
Sea ice | Low | Connor Corridor | 2012 | Thule | Thule | 7.4 |  | redesign along contemporaneous (within ~6 hr) Sentinal 3a groundtrack; create latlon file
Sea ice | Low | Northwest Passage | 2010 | Thule | Thule | 7.4
Land ice | Baseline | ICESat-2 North / CryoSat-2 SARIn | 2015 | Thule | Thule | 7.9 | 0484,1246,0621,0057,0880,0316
Land ice | Baseline | Zachariæ-79N | 2016 | Longyearbyen | Thule | 7.9 | 0105,0224,0239,0343,1325,1340
Land ice | Baseline | Northwest Coastal A | 2016 | Thule | Thule | 7.6
Land ice | Baseline | ICESat-2 Central | 2016 | Kangerlussuaq | Kangerlussuaq | 8 | 1169,1022,1047,0041,0422,1245,0239,0178
Land ice | Baseline | Thomas-Jakobshavn 01 | 2016 | Kangerlussuaq | Kangerlussuaq | 8.4 | 0323,0300,0047,0285,0070,0204
Land ice | Baseline | Jakobshavn-Eqip-Store | 2015 | Kangerlussuaq | Kangerlussuaq | 8.4 | 0085,1320,1282,0166,0189,0032,0151,1305
Land ice | Baseline | K-EGIG-Summit | 2015 | Kangerlussuaq | Kangerlussuaq | 8.1 | 0055,0017,0270
Land ice | Baseline | Helheim-Kangerdlugssuaq | 2016 | Kangerlussuaq | Kangerlussuaq | 7.9 | 0263
Land ice | Baseline | Southeast Coastal | 2016 | Kangerlussuaq | Kangerlussuaq | 8.2
Land ice | Baseline | Southwest Coastal A | 2016 | Kangerlussuaq | Kangerlussuaq | 8
Land ice | High | North Ellesmere 01 | 2014 | Thule | Thule | 7.5
Land ice | High | South Ellesmere 01 | 2014 | Thule | Thule | 7.7
Land ice | High | Alexander-Petermann 01 | 2014 | Thule | Thule | 7.9 | 1306,0071,1321,0220,1336,0250,1342,0226,0092
Land ice | High | Humboldt 01 | 2014 | Thule | Thule | 7.3 | 0071,0324,0086,0339,0101,0354,0315
Land ice | High | North Flux 02 | new | Thule | Thule | 7.9 | 0092,0211,0330,1312,0205,0239,0001,1306
Land ice | High | North Glaciers 02 Prime | 2014 | Thule | Thule | 7.7 | 0220,0309,0219
Land ice | High | North Central Gap 01 | 2015 | Thule | Thule | 7.8
Land ice | High | North Central Gap 03 | 2013 | Thule | Thule | 7.9
Land ice | High | Northwest Coastal C | 2014 | Thule | Thule | 7.7
Land ice | High | Unmanaq B | 2016 | Kangerlussuaq | Kangerlussuaq | 8
Land ice | High | Geikie 01 | 2014 | Kangerlussuaq | Kangerlussuaq | 8.2 |  | use improved Vestfjord CL from 2015 Geikie 02
Land ice | High | Helheim-Kangerdlugssuaq Gap B | 2016 | Kangerlussuaq | Kangerlussuaq | 8.3
Land ice | High | OSU Clusters | 2014 | Kangerlussuaq | Kangerlussuaq | 7.4 | 0040,0181
Land ice | High | Southeast Glaciers 01 | 2015 | Kangerlussuaq | Kangerlussuaq | 7.9 | 0166,0040,0159
Land ice | High | ICESat-2 South | new | Kangerlussuaq | Kangerlussuaq | 8.1 | 1222,0300,0681,0277,0658,1039
Land ice | High | Southwest Glaciers 01 | 2014 | Kangerlussuaq | Kangerlussuaq | 8.1 | 0040,0412,0047,0159,0300
Land ice | Medium/High | Northeast Grid 05 | new | Thule | Thule | 7.6 | 0263,0025
Land ice | Medium | Devon-Barnes 01 | 2015 | Thule | Thule | 7.6
Land ice | Medium | North Glaciers 01 | 2015 | Thule | Thule | 8 | 0278
Land ice | Medium | Northeast Glaciers 02 | 2014 | Thule | Thule | 7.6
Land ice | Medium | North Central Gap 02 | 2015 | Thule | Thule | 7.8
Land ice | Medium | Northwest Glaciers 01 | 2015 | Thule | Thule | 7.7
Land ice | Medium | Penny 01 | 2015 | Kangerlussuaq | Kangerlussuaq | 6.2 | 0160,0041,0413,0294,0271,0390,0018
Land ice | Medium | Geikie 02 | 2015 | Kangerlussuaq | Kangerlussuaq | 8.2 | 0010,0382 | confirm coordinates of Renland core site are current
Land ice | Medium | Southeast Flank 01 | 2015 | Kangerlussuaq | Kangerlussuaq | 7.3
Land ice | Medium | Southeast Glaciers 02 | 2015 | Kangerlussuaq | Kangerlussuaq | 6.5
Land ice | Medium | Southwest Coastal B | 2015 | Kangerlussuaq | Kangerlussuaq | 8.1
Land ice | Low | Alaska Glaciers | 2005 | Fairbanks | Fairbanks | 7.7
Land ice | Low | Humboldt 02 | new | Thule | Thule | 7.4 | 0190,1306,0205,1321,0220,1336,0196
Land ice | Low | Northwest Glaciers 02 | 2014 | Thule | Thule | 7.1
Land ice | Low | Northwest Coastal B | 2014 | Thule | Thule | 7.1
Land ice | Low | Northwest Coastal 06 | new | Thule | Thule | 7.5
Land ice | Low | Northwest Coastal 07 | new | Thule | Thule | 7.4
Land ice | Low | Jakobshavn 02 | 2015 | Kangerlussuaq | Kangerlussuaq | 6.3 | 0181
Land ice | Low | Umanaq A | 2012 | Kangerlussuaq | Kangerlussuaq | 7.2
Land ice | Low | East Glaciers 01 | 2016 | Kangerlussuaq | Kangerlussuaq | 8.1 | 0412, 50307, 50879
Land ice | Low | Helheim-Kangerdlugssuaq Gap A | 2012 | Kangerlussuaq | Kangerlussuaq | 8