## Overview
Operation IceBridge Overall Summary Statistics Worksheet
Project Totals | as of 1/10/2018 | Number of days | [7 empty] | Number of Flights |  |  |  |  | Aircraft Hours |  | Distances (km) | [7 empty] | Notes
|  | Total | Flight | WX | Unpln'd Maint | Plan'd Maint | Crew | (Un)Pack | External | Total | Science | Transit | E/C/FCF | Non-OIB | Flight | Science | Total Flight | Science | ICESat | ICESat-2 | CryoSat-2 | EnviSat | Sentinal-3a/b | TanDEM-X
|  | 1672 | 1047.97 | 150.8 | 136.1 | 36.55 | 156.3 | 56.38 | 121.9 | 1188 | 881 | 185 | 109 | 21 | 7421.56 | 4150.4 | 3654457.27 | 1949661.16 | 245882.47 | 95019.36 | 44548.96 | 2209.49 | 4944.9 | 2628.7
Campaign | Platform | Number of days | [7 empty] | Number of Flights |  |  |  |  | Aircraft Hours |  | Distances (km)
|  | Total | Flight | WX | Unpln'd Maint | Plan'd Maint | Crew | (Un)Pack | External | Total | Science | Transit | E/C/FCF | Non-OIB | Flight | Science | Total Flight | Science | ICESat | ICESat-2 | CryoSat-2 | EnviSat | Sentinal-3a/b | TanDEM-X
Arctic 2009 | P-3 | 38 | 25.7 | 3 | 3.3 | 0 | 3 | 0 | 4 | 23 | 20 | 2 | 1 | 4 | 180.2 | 105.95 | 74772.53 | 48774 | 26450.26 | 0 | 0 | 2209.49 | 0 | 0
| DHC-3 (UAF) | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 54.8 | 41.52 | 1841 | 1841 |  | 0 | 0 | 0 | 0 | 0 | *Total flight distance not reported, science distance used in lieu
Antarctic 2009 | DC-8 | 45 | 28 | 6 | 0 | 2 | 4 | 2 | 5 | 29 | 21 | 5 | 3 | 0 | 250.9 | 92.94 | 155304.95 | 155304 | 6937.59 | 0 | 0 |  | 0 | 0
| BT-67 (UTIG) | 59 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 19 | 0 | 2 | 0 | 127.37 | 101.34 | 29905 | 29905 |  | 0 |  | 0 | 0 | 0 | *Total flight distance not reported, science distance used in lieu
Arctic 2010 | DC-8 | 33 | 19 | 7 | 0 | 0 | 2 | 0 | 7 | 20 | 16 | 4 | 2 | 0 | 128 | 88.14 | 80458.23 | 43461.7 | 9360.01 | 0 | 1340.85 |  | 0 | 0 | Area based off of ATM and LVIS coverage
| P-3 | 24 | 18 | 2 | 0 | 0 | 1 | 4 | 3 | 18 | 13 | 3 | 3 | 0 | 110.9 | 67.4 | 40513.8 | 29731.34 | 3485.46 | 0 | 0 | 0 | 0 | 0 | Area based off of ATM and LVIS coverage
| DHC-3 (UAF) | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 39.3 | 19.4 | 3213.48 | 3213.48 |  | 0 | 0 | 0 | 0 | 0 | Differences in flight data reported at ESPO vs LIDAR data available at NSIDC for dates, distances and times. *Total flight distance not reported, science distance used in lieu
Antarctic 2010 | DC-8 | 38 | 16.75 | 11.25 | 8 | 0 | 2 | 1.5 | 0.5 | 18 | 10 | 5 | 3 | 0 | 150.2 | 34.68 | 75857.92 | 15377.45 | 3720.67 | 0 | 2261.29 | 0 | 0 | 0 | Area based off of ATM and LVIS coverage
| BT-67 (UTIG) | 72 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 36 | 4 | 0 | 0 | 69.5 | 62.37 | 64392 | 64392 |  | 0 |  | 0 | 0 | 0 | Differences in flight data reported at ESPO vs LIDAR data available at NSIDC for dates, distances and times. *Total flight distance not reported, science distance used in lieu
Arctic 2011 | P-3 | 67 | 44.5 | 2 | 7.5 | 0 | 3 | 3 | 10 | 46 | 38 | 3 | 5 | 0 | 299.4 | 184.3 | 126661.98 | 85330.9 | 15030.83 | 0 | 2057.57 |  | 0 | 0
| B-200 (LVIS) | 29 | 19 | 1 | 5 | 0 | 1 | 0 | 4 | 25 | 18 | 5 | 2 | 1 | 109.1 | 79.97 | 34841.68 | 24520.76 | 4933.73 | 0 |  | 0 | 0 | 0
| BT-67 (UTIG) | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 35.68 | 35.68 | 11704 | 11704 |  | 0 |  | 0 | 0 | 0 | No flight reports available at ESPO at time of last update, all stats based off of data available at NSIDC (5/31/2013). *Total flight distance not reported, science distance used in lieu. Same with hours
| DHC-3 (UAF) | 12 | 10.99 | 1 | 0 | 0 | 0 | 0 | 0 | 31 | 18 | 13 | 0 | 0 | 69.9 | 21.13 | 12863.99 | 3505.26 | 0 | 0 | 0 | 0 | 0 | 0
Antarctic 2011 | DC-8 | 46 | 30 | 9 | 1 | 1 | 4 | 2 | 1 | 31 | 24 | 5 | 2 | 0 | 308.6 | 106.32 | 176484.49 | 49226.16 | 7815.44 | 0 | 2415.01 | 0 | 0 | 0
| G-V (LVIS) | 28 | 12.9 | 8.1 | 0 | 0 | 4 | 2 | 0 | 17 | 11 | 4 | 2 | 0 | 126.9 | 62.44 | 91455.46 | 11268.4 | 1353.81 | 0 | 0 | 0 | 0 | 0
| BT-67 (UTIG) | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 20 | 1 | 2 | 0 | 127.8 | 65.44 | 7814 | 20685.67 |  | 0 |  | 0 | 0 | 0
Arctic 2012 | P-3 | 75 | 47.25 | 1 | 5.25 | 6.5 | 8 | 3 | 7 | 48 | 43 | 2 | 3 | 0 | 346.12 | 241.35 | 151841.78 | 111745.05 | 25355.73 | 0 | 7746.92 |  | 0 | 0
| HU-25 (LVIS) | 19 | 14 | 0 | 2 | 0 | 0 | 0 | 3 | 14 | 11 | 3 | 0 | 0 | 73.87 | 50.74 | 45636.98 | 12064.46 | 5711.57 | 0 | 0 | 0 | 0 | 0
| DHC-3 (UAF) | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 0 | 0 | 119.3 | 86.58 | 3613.45 | 3613.45 | 0 | 0 | 0 | 0 | 0 | 0 | No data at NSIDC after May 24th, August is all prelim data, *Total flight distance not reported, science distance used in lieu
Antarctic 2012 | DC-8 | 31 | 22 | 4 | 1 | 2 | 4 | 2 | 0 | 26 | 20 | 7 | 0 | 4 | 215.7 | 64.1 | 150362.03 | 29678.3 | 1494.56 | 0 | 2026.09 | 0 | 0 | 0 | Science distances/times and areas based off of ATM wide-scan only
| BT-67 (UTIG) | 54 | 20 | 25.5 | 0 | 0 | 0 | 5.5 | 3 | 27 | 24 | 4 | 5 | 0 | 133.23 | 126.53 | 39934.68 | 38211.58 | 1093.79 | 0 | 0 | 0 | 0 | 0
Arctic 2013 | P-3 | 46 | 29.3 | 1 | 6.7 | 0 | 6 | 1 | 4 | 30 | 26 | 3 | 3 | 2 | 210.9 | 146.4 | 100503 | 67690.6 | 14956.2 | 0 | 3459.4 | 0 | 0 | 0
| DHC-3 (UAF) | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 50.8 | 50.8 | 7247 | 7247 |  | 0 | 0 | 0 | 0 | 0
Seasonal 2013 | C-130 (LVIS) | 17 | 13.38 | 1.25 | 1.75 | 0 | 1 | 0.13 | 2.5 | 14 | 9 | 3 | 2 | 0 | 88.44 | 52.09 | 38429 | 27769 | 2896 | 0 | 2900 | 0 | 0 | 0
Antarctic 2013 | P-3 | 21 | 19 | 2 | 0 | 0 | 0 | 0 | 4 | 20 | 6 | 9 | 5 | 0 | 128.2 | 43.1 | 67660.95 | 19955.3 | 0 | 138.9 | 1766.8 | 0 | 0 | 0
| BT-67 (UTIG) | 14 | 8 | [6 empty] | 9 | 7 | 0 | 2 | 0 | 47.1
Arctic 2014 | P-3 | 75 | 51 | 5.5 | 2 | 0 | 43 | 2 | 14.5 | 53 | 46 | 5 | 2 | 0 | 372.5 | 300.4 | 174264.1 | 139085.2 | 21752.8 | 4263.2 | 3172.3 | 0 | 0 | 0
| DHC-3 (UAF) | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 75.5 | 75.5 | 11256 | 11256 | 0 | 0 | 0 | 0 | 0 | 0
| C-130 (ARISE) | 33 | 19.7 | 1.3 | 7 | 1 | 5 | 1 | 0 | 21 | 17 | 2 | 2 | 0 | 155.7 | N/A | 56705 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | Some fields not given as a direct comparison with other OIB flights is inappropriate, due to instrument/goal differences between ARISE and OIB flights
Antarctic 2014 | P-3 | 51 | 29 | 4 | 8 | 2 | 5 | 4 | 0 | 29 | 22 | 4 | 3 | 2 | 275 | 104.9 | 185942 | 48568.7 | 6946.85 | 1411.22 | 3211.37 | 0 | 0 | 0
Arctic 2015 | C-130 | 67 | 41 | 2 | 12 | 0 | 6 | 2 | 7 | 44 | 33 | 5 | 6 | 0 | 288.9 | 227.6 | 139755.62 | 105378.8 | 13353.29 | 2363.15 | 1290.84 | 0 | 0 | 0
| DHC-3 (UAF) | [8 empty] | 13 | [14 empty] | Number of flights estimated from kml
Arctic Fall 2015 | HU-25C | 34 | 19.5 | 8 | 3 | 0 | 2 | 1.5 | 1 | 30 | 22 | 7 | 1 | 0 | 97.9 | 72.3 | 65779.2 | 53502 | 6795.1 | 1500.1 | 214.8 | 0 | 0 | 0
Antarctic 2015 | G-V | 49 | 25 | 1 | 0.2 | 14.05 | 7 | 0.75 | 1 | 23 | 16 | 6 | 5 | 4 | 218.8 | 141.6 | 159625 | 110521 | 5220 | 0 | 854 | 0 | 0 | 0
Arctic 2016 | NOAA P-3 | 39 | 22.2 | 4 | 7.8 | 1 | 4 | 1 | 2 | 23 | 16 | 4 | 3 | 0 | 150.1 | 101.9 | 72208.79 | 47179.7 | 7169.09 | 1842.74 | 698.2 | 0 | 737.1 | 0
| DHC-3 (UAF) | [8 empty] | 15 | [14 empty] | Number of flights estimated from kml
Arctic Summer 2016 | HU-25 | 38 | 26 | 5 | 2 | 0 | 3 | 2 | 2 | 42 | 23 | 16 | 3 | 0 | 126.9 | 60.5 | 87021.87 | 44770 | 4609.63 | 1516.79 | 863.03 | 0 | 0 | 0
Antarctic 2016 | DC-8 | 41 | 28 | 5 | 1 | 1 | 5 | 3 | 0 | 30 | 24 | 4 | 2 | 0 | 307.1 | 107.2 | 210685.38 | 49633.6 | 4126.26 | 5441.18 | 3326.19 | 0 | 0 | 0
Arctic 2017 | P-3 | 68 | 46.2 | 6 | 2 | 0 | 4.8 | 1 | 11 | 47 | 40 | 4 | 3 | 0 | 332 | 261.4 | 155868 | 121028.2 | 16571 | 11539 | 3222 | 0 | 2026 | 0
| DHC-3 (UAF) | [8 empty] | 7 | [14 empty] | Number of flights estimated from kml
Arctic Summer 2017 | HU-25C | 13 | 10 | 3 | 0 | 0 | 0 | 0 | 4 | 13 | 6 | 6 | 1 | 0 | 39.5 | 13.5 | 25456.77 | 6250.5 | 0 | 0 | 0 | 0 | 0 | 0
| B-200 (LVIS) | 35 | 24 | 6 | 2 | 0 | 4 | 0 | 1 | 28 | 15 | 8 | 5 | 0 | 128.65 | 87.49 | 44444.71 | 34400
Antarctic 2017 | P-3 | 38 | 21 | 3 | 3 | 4 | 5 | 2 | 4 | 22 | 11 | 7 | 4 | 0 | 156 | 29 | 85106 | 13427 | 0 | 2855.78 | 0 | 0 | 0 | 2628.7
| DC-3C (Basler) | 27 | 15.1 | 4.9 | 0.5 | 0 | 0.5 | 3 | 3 | 22 | 16 | 0 | 6 | 0 | 107.9 |  | 33880
Arctic 2018 | P-3 | 45 | 27.2 | 2 | 9.6 | 0 | 4 | 1 | 5.2 | 28 | 22 | 4 | 5 | 2 | 190.4 | 128.8 | 90088.5 | 59634.4 | 10587.8 | 7319 | 431.5 | 0 | 639 | 0
DHC-3 (UAF)
Antarctic 2018 | DC-8 | 46 | 31 | 2 | 5 | 1 | 6 | 3 | 0 | 31 | 24 | 5 | 2 | 0 | 296.8 | 87.2 | 214930 | 40373.6 | 55.6 | 20977.5 | 0 | 0 | 531.5 | 0
Arctic 2019 | P-3 | 45 | 27.2 | 2 | 9.6 | 0 | 4 | 1 | 5.2 | 28 | 22 | 4 | 5 | 2 | 190.4 | 128.8 | 90088.5 | 59634.4 | 10587.8 | 7319 | 431.5 | 0 | 639 | 0
| DHC-3 (UAF) | 47 | 32 | 1 | 8 | 1 | 5 | 2 | 1 | 33 | 24 | 6 | 3 | 0 | 225.8 | 145.9 | 107680.85 | 67551.7 | 4905.9 | 21040.6 | 859.3 | 0 | 372.3 | 0
Arctic Summer 2019 | G-V | 26 | 13.1 | 0 | 11.9 | 0 | 0 | 0 | 2 | 14 | 10 | 3 | 1 | 0 | 83.5 | 45.7 | 50357.6 | 21250.5 | 2605.7 | 5491.2 | 0 | 0 | 0 | 0

## Legend
WORKSHEET LEGEND
Number of Days
Total | Total number of days deployed
Flight | Flight day
WX | Down day due to weather
Unpln'd Maint | Down day due to nplanned maintenance
Plan'd Maint | Down day due to planned maintenance
Crew | Down day due to crew reasons/hard day down
(Un) Pack | Packing/Unpacking day
External | Down day due to external factors, such as: airport closed, a foreign government strike, etc.
Number of Flights
Total | Total number of OIB funded flights
Science | Science Flights
Transit | Transit Flights
E/C/FCF | ECF, PCF or FCF flight. Calibration flights as well. Essentially any other type of flight that is funded by OIB, but not a transit or science flight.
Non-OIB | Flights that are not funded by OIB, such as maintenance flights or aircraft check flights
Aircraft Hours
Flight | Total number of flight hours, based primarily upon ESPO database numbers
Science | Total number of flight hours which science data was gathered, primarily based upon lidar instrument data (ATM, LVIS, Rigel)
Distances (km)
Science | Distance on the ground, of data collected; same datasets and criteria used as with science time field
Area (sq Km)
Area | Areas based off of coverage of available LIDAR data for each flight. POS/AV GPS data must be available to calculate altitude above ground
*Any red highlighted field has missing/incmplete data
*Science Times for P-3 & DC-8 from 2009/10 campaigns do not yet include data from the high-altitude LVIS portions of the flights
*P-3/DC-8 Areas are based off of ATM instrument only